# 90-Day Marketing Launch Roadmap – Study in France Recruitment Agency

This roadmap outlines a structured 90‑day marketing launch plan designed for a new student recruitment agency focused on France. The goal is to build credibility, generate qualified leads, and convert early students into enrollments while establishing a trusted brand.

# Phase 1 – Foundation & Credibility (Days 1–30)

Set up brand assets: logo, color palette, typography, brand messaging.

Launch website with core pages: Home, Study in France, Programs, Visa Process, Accommodation, Contact.

Implement AI eligibility chat on website using Groq.

Create Instagram, YouTube, and LinkedIn accounts.

Prepare 15–20 short-form educational videos using HeyGen.

Create initial blog articles: France visa process, cost of living, top business schools in France.

Publish 3–4 Instagram posts per week explaining studying in France.

Run small awareness ads ($10–15/day) introducing France as a study destination.

Collect early leads via AI eligibility tool.

Start building email and WhatsApp lead lists.

# Phase 2 – Education & Lead Generation (Days 31–60)

Increase content production: 4–5 reels per week.

Topics: Campus France interview tips, student visa process, housing in France, career outcomes.

Run targeted Instagram ads promoting the AI eligibility assessment.

Launch first webinar: 'How Indian Students Can Study in France in 2026'.

Build program-specific landing pages for key universities.

Send weekly email newsletters to collected leads.

Publish student life content from France (city tours, campus clips).

Begin retargeting campaigns for website visitors.

Track key metrics: lead cost, engagement, conversion rate.

# Phase 3 – Conversion & Authority (Days 61–90)

Scale winning ad creatives identified in Phase 2.

Increase ad budget gradually to $20–30/day.

Publish student testimonial videos or interviews.

Launch parent-focused content explaining safety, visa success rates, and housing.

Host second webinar focusing on admissions and application strategy.

Develop partnerships with student ambassadors in France.

Promote limited application timelines for upcoming intake.

Implement structured follow-up via WhatsApp and email automation.

Track final funnel metrics: counselling calls, applications started, enrollments.

# Expected Results After 90 Days

• 5,000–10,000 social media followers
• 500–800 leads generated
• 100–150 counselling calls
• 40–60 applications started
• 15–25 enrolled students

# Estimated Budget

Content production (HeyGen + editing): $150–300
Ad spend for 90 days: $900–1,500
Webinar tools and marketing tools: $50–100
Total estimated marketing investment: $1,100–1,900